## Project Schedule
CIVE 202 - Project #4: NRI Risk Analysis
Nick Meier & Bryce Ripley
Project Timeline: March 24 - April 21, 2026
TASK | ASSIGNEE | DEPENDS ON | START | END | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
[5 empty] | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
Project Setup and Planning
Scope of Work | Bryce |  | 2026-03-24 | 2026-04-03 | bar: T to S; S to S; S to S
Gantt Chart | Nick | Scope of Work | 2026-03-24 | 2026-04-10 | bar: T to S; S to S
Define Levels of Risk | Bryce | Scope of Work | 2026-04-03 | 2026-04-10 | bar: F to S; S to S
Data Acquisition and Cleaning
Download NRI Data (2 states) | Both | Define Levels of Risk | 2026-04-10 | 2026-04-17 | bar: F to S
Download NRI Metadata Files | Both | Define Levels of Risk | 2026-04-10 | 2026-04-17 | bar: F to S
Download SVI Dataset (ATSDR) | Both | Define Levels of Risk | 2026-04-10 | 2026-04-17 | bar: F to S
Clean and Organize Data | Nick | Download NRI Data | 2026-04-13 | 2026-04-17 | bar: S to S
Handle Missing/NA Values | Nick | Clean and Organize Data | 2026-04-13 | 2026-04-17 | bar: S to S
Python Analysis Development
GeoPandas Tools Investigation | Nick | Download NRI Data | 2026-04-10 | 2026-04-17 | bar: F to S
Join NRI + SVI Datasets | Both | Clean and Organize Data | 2026-04-14 | 2026-04-18 | bar: S to S; T to S
Build Alternative Risk Index | Bryce | Define Levels of Risk | 2026-04-15 | 2026-04-19 | bar: S to S; W to S
Summary Tables / Figures (NRI def.) | Bryce | Join NRI + SVI Datasets | 2026-04-16 | 2026-04-19 | bar: S to S; T to S
Summary Tables / Figures (Alt. def.) | Bryce | Build Alternative Risk Index | 2026-04-16 | 2026-04-20 | bar: S to S; T to M
Mapping
GeoPandas Risk Map | Nick | GeoPandas Investigation, Join NRI + SVI | 2026-04-17 | 2026-04-20 | bar: S to S; F to M
Code Documentation
Annotated Code Document (ACD) | Both | All analysis tasks | 2026-04-18 | 2026-04-20 | bar: S to S; S to M
GitHub Repository Setup & Finalize | Nick | Annotated Code Document | 2026-04-18 | 2026-04-20 | bar: S to S; S to M
Technical Report Writing
Methodology & Risk Definitions | Bryce | Define Levels of Risk | 2026-04-17 | 2026-04-19 | bar: S to S; F to S
Compare NRI vs. Alt. Risk Results | Both | Summary Tables / Figures | 2026-04-18 | 2026-04-20 | bar: S to S; S to M
Ethical Implications Discussion | Bryce | Compare NRI vs. Alt. Results | 2026-04-19 | 2026-04-20 | bar: S to S; S to M
Final Review and Submission
Final Review & Submit to Canvas | Both | All tasks | 2026-04-20 | 2026-04-21 | bar: S to S; S to T
Legend:
Project Setup and Planning
Data Acquisition and Cleaning
Python Analysis Development
Mapping
Code Documentation
Technical Report Writing
Final Review and Submission